## Implementation Plan
Project Start Date | 2026-09-21 |  | Production Go-Live Target | 2027-07-30 |  | Client Review Window (days) | 5 |  | ROM Contingency | 20%
Change the yellow start date or target date. Task dates recalculate using Monday-Friday workdays and optional dates on the Holidays sheet. | [7 empty] | Target Status | ON OR BEFORE TARGET
WBS | Task Name | Effort Hours | Duration (Working Days) | Start | Finish | Predecessor | Resource Names | Outcome / Deliverable | Status | Release
1 | Production GIS Application Implementation and Migration | 6994 | 289 | 2026-09-21 | 2027-11-11 |  |  | Usable production release by July 2027; specialist workflows continue afterwards.
1.1 | Confirm Scope and Priorities | 240 | 15 | 2026-09-21 | 2026-10-09 |  |  | Summary of confirm scope and priorities activities. |  | Scope Baseline
1.1.1 | Confirm required tools, datasets and first production release | 160 | 10 | 2026-09-21 | 2026-10-02 |  | PM, PD, Design, Frontend, Backend | Prioritised production scope, dataset list and documented assumptions. | Not Started | Scope Baseline
1.1.2 | Approve scope baseline and change-control approach | 80 | 5 | 2026-10-05 | 2026-10-09 | 1.1.1 | PM, PD | Single client approval gate; subsequent changes are assessed through change control. | Not Started | Scope Baseline
1.2 | Establish Production Foundation | 492 | 51 | 2026-10-12 | 2026-12-22 |  |  | Summary of establish production foundation activities. |  | Foundation
1.2.1 | Set up environments and automated deployment | 120 | 15 | 2026-10-12 | 2026-10-30 | 1.1.2 | Backend, Frontend | Development, test and production environments with repeatable deployment. | Not Started | Foundation
1.2.2 | Create PostGIS and backend application foundation | 200 | 20 | 2026-11-02 | 2026-11-30 | 1.2.1 | Backend, Frontend, Design, PM | Production database and deployable backend application foundation. | Not Started | Foundation
1.2.3 | Implement authentication, configuration and operations | 172 | 15 | 2026-12-01 | 2026-12-21 | 1.2.2 | Backend, Frontend, PM | Authentication, basic authorisation, logging, monitoring, backups and configuration. | Not Started | Foundation
1.2.4 | Secure production foundation ready | 0 | 0 | 2026-12-22 | 2026-12-22 | 1.2.3 |  | Milestone: a secure, mostly empty application can be deployed reliably. | Not Started | Foundation
1.3 | Build Data Pipeline and Core API | 368 | 41 | 2026-12-23 | 2027-02-23 |  |  | Summary of build data pipeline and core api activities. |  | Data/API Ready
1.3.1 | Build spatial data loading and publishing pipeline | 128 | 20 | 2026-12-23 | 2027-01-22 | 1.2.4 | Backend, PM | Validated data loading into PostGIS, catalogue publication and cached MapLibre tiles. | Not Started | Data/API Ready
1.3.2 | Build shared spatial API and ArcGIS authoring integration | 240 | 20 | 2027-01-25 | 2027-02-22 | 1.3.1 | Backend, Design, .NET | Shared query, search, identify and spatial operations plus configuration authoring support. | Not Started | Data/API Ready
1.3.3 | Publish initial production datasets | 0 | 0 | 2027-02-23 | 2027-02-23 | 1.3.2 |  | Milestone: representative public and restricted datasets are available end to end. | Not Started | Data/API Ready
1.4 | Build the Frontend Application Shell | 216 | 31 | 2026-12-23 | 2027-02-09 |  |  | Summary of build the frontend application shell activities. |  | Working Application
1.4.1 | Build MapLibre shell, ribbon, map and empty panels | 136 | 15 | 2026-12-23 | 2027-01-15 | 1.2.4 | Frontend, Backend, Design, PM | MapLibre application with Home, Map, Tools and Advanced Tools structure. | Not Started | Working Application
1.4.2 | Connect login, catalogue, map data and user state | 80 | 10 | 2027-01-18 | 2027-02-01 | 1.4.1 | Frontend | Authenticated working map connected to published data and shared services. | Not Started | Working Application
1.4.3 | Verify deployable working application | 0 | 5 | 2027-02-02 | 2027-02-08 | 1.4.2 | Frontend, Backend, Testing | Working application in each environment, ready for incremental tools. | Not Started | Working Application
1.4.4 | Frontend foundation ready | 0 | 0 | 2027-02-09 | 2027-02-09 | 1.4.3 |  | Milestone: working application foundation available early in delivery. | Not Started | Working Application
1.5 | Deliver Core Map Tools | 1120 | 51 | 2027-02-24 | 2027-05-11 |  |  | Summary of deliver core map tools activities. |  | Core Toolset
1.5.1 | Search, layer catalogue, layer list and map navigation | 560 | 20 | 2027-02-24 | 2027-03-24 | 1.3.3 | Frontend, Backend, Design, Testing | Users can locate an area and manage authorised map layers. | Not Started | Core Toolset
1.5.2 | Identify, query, table view, metadata and filtering | 560 | 25 | 2027-03-25 | 2027-05-03 | 1.5.1 | Frontend, Backend, Design, Testing | Users can inspect, query, filter and work with map features and attributes. | Not Started | Core Toolset
1.5.3 | Core tools demonstration and acceptance window | 0 | 5 | 2027-05-04 | 2027-05-10 | 1.5.2 | PM, PD | First meaningful consolidated client review and acceptance point. | Not Started | Core Toolset
1.5.4 | Core map tools production-ready | 0 | 0 | 2027-05-11 | 2027-05-11 | 1.5.3 |  | Milestone: essential map workflow is ready for release. | Not Started | Core Toolset
1.6 | Deliver General GIS Tools | 1680 | 35 | 2027-05-12 | 2027-06-30 |  |  | Summary of deliver general gis tools activities. |  | Main Toolset
1.6.1 | Measurement, drawing and editing | 400 | 10 | 2027-05-12 | 2027-05-25 | 1.5.4 | Frontend, Backend, Design, Testing | Measurement and reusable drawing/editing capability. | Not Started | Main Toolset
1.6.2 | Buffering, intersects, filters and property calculations | 520 | 12 | 2027-05-26 | 2027-06-10 | 1.6.1 | Frontend, Backend, Testing | General spatial analysis used by VicPlan and Radius workflows. | Not Started | Main Toolset
1.6.3 | Projects, sharing, upload, export and printing | 760 | 12 | 2027-06-11 | 2027-06-29 | 1.6.2 | Frontend, Backend, Design, Testing | Saved work, secure data exchange and production map outputs. | Not Started | Main Toolset
1.6.4 | Main production toolset complete | 0 | 0 | 2027-06-30 | 2027-06-30 | 1.6.3 |  | Milestone: main tools are available before migration and launch. | Not Started | Main Toolset
1.7 | Migration, Acceptance and Launch | 1958 | 67 | 2027-05-12 | 2027-08-13 |  |  | Summary of migration, acceptance and launch activities. |  | July 2027 Production
1.7.1 | Prepare documentation and operational handover | 200 | 15 | 2027-05-12 | 2027-06-01 | 1.5.4 | Frontend, Backend, .NET, PM | User, administrator, support and technical material prepared in parallel with tool delivery. | Not Started | July 2027 Production
1.7.2 | Production hardening, regression and migration rehearsal | 352 | 10 | 2027-07-01 | 2027-07-14 | 1.6.4 | Frontend, Backend, Testing | Performance, security, accessibility, regression and final data/configuration rehearsal. | Not Started | July 2027 Production
1.7.3 | Consolidated UAT, training and final migration | 80 | 9 | 2027-07-15 | 2027-07-27 | 1.7.2 | Frontend, Backend, Testing, PM, PD | Business acceptance, trained users/support staff and production data ready for cutover. | Not Started | July 2027 Production
1.7.4 | Delivery contingency and remediation allowance | 1166 | 0 | 2027-07-28 | 2027-07-28 | 1.7.3 | Frontend, Backend, Design, .NET, Testing, PM, PD | Budget contingency retained in the ROM; no separate delay is forced into the baseline schedule. Any use of contingency is managed through delivery forecasts. | Not Started | July 2027 Production
1.7.5 | Environment promotion and production cutover | 80 | 1 | 2027-07-29 | 2027-07-29 | 1.7.4 | Frontend, Backend | Deploy, migrate, verify and switch the supported production service. | Not Started | July 2027 Production
1.7.6 | Production Go Live | 0 | 0 | 2027-07-30 | 2027-07-30 | 1.7.5 |  | Milestone: usable application, main tools and migration complete by the July 2027 target. | Not Started | July 2027 Production
1.7.7 | Warranty and hypercare | 80 | 10 | 2027-08-02 | 2027-08-13 | 1.7.6 | Frontend, Backend | Post-launch monitoring and prioritised remediation. | Not Started | July 2027 Production
1.8 | Deliver Specialist Workflows After Launch | 920 | 64 | 2027-08-16 | 2027-11-11 |  |  | Summary of deliver specialist workflows after launch activities. |  | Post-Launch Enhancements
1.8.1 | Planning and heritage workflows | 400 | 25 | 2027-08-16 | 2027-09-17 | 1.7.7 | Frontend, Backend, Design, Testing | Amendment Search, Heritage Overlay Search, Definition Plan and AMG Coordinate Tool. | Not Started | Post-Launch Enhancements
1.8.2 | Advanced summary workflows | 320 | 20 | 2027-09-20 | 2027-10-15 | 1.8.1 | Frontend, Backend, Design, Testing | Redevelopment, Broadhectare, HDD and Heritage Bushfire summaries. | Not Started | Post-Launch Enhancements
1.8.3 | Imagery, time slider and Street View | 200 | 13 | 2027-10-18 | 2027-11-03 | 1.8.2 | Frontend, Backend, Design, Testing | Remaining imagery, temporal and external map integrations. | Not Started | Post-Launch Enhancements
1.8.4 | Post-launch enhancement release | 0 | 5 | 2027-11-04 | 2027-11-10 | 1.8.3 | Frontend, Backend, Testing | Regression and controlled production enablement of specialist tools. | Not Started | Post-Launch Enhancements
1.8.5 | Implementation complete | 0 | 0 | 2027-11-11 | 2027-11-11 | 1.8.4 | PM, PD | Milestone: agreed post-launch enhancements delivered and handed over. | Not Started | Post-Launch Enhancements
Formulas:
Duration (Working Days) = NETWORKDAYS.INTL([Start],[Finish],1,Holidays!$A2:A100)
Start = MIN([Start, row below]:E46)
Start = IF([Predecessor]="",B1,WORKDAY.INTL(INDEX($F:$F,MATCH([Predecessor],$A:$A,0)),1,1,Holidays!$A2:A100))
Finish = MAX([Finish, row below]:F46)
Finish = IF([Duration (Working Days)]=0,[Start],WORKDAY.INTL([Start],[Duration (Working Days)]-1,1,Holidays!$A2:A100))
Note on B1: Change this cell to reschedule the whole predecessor-driven plan.
Note on E1: Default is the final working day of July 2027. The Target Status compares Go Live with this date.
Note on H1: Used for the two consolidated client review gates.

## Holidays
Excluded Work Date | Description
2026-11-03 | Melbourne Cup Day
2026-12-25 | Christmas Day
2026-12-28 | Boxing Day substitute
2027-01-01 | New Year's Day
2027-01-26 | Australia Day
2027-03-08 | Labour Day
2027-03-26 | Good Friday
2027-03-29 | Easter Monday
2027-04-26 | ANZAC Day substitute
2027-06-14 | King's Birthday

## Plan Notes
Topic | Detail
Delivery objective | A usable migrated production application containing the core and general GIS tools is targeted for July 2027.
Map technology | The production map client is MapLibre.
Working foundation | The secure platform, data path and empty application shell are delivered early so the application remains deployable throughout development.
Pre-launch tools | Search, catalogue, layer management, identify, query, table, navigation, metadata/filtering, measurement, drawing, spatial analysis, projects, upload/export and printing are scheduled before Go Live.
Post-launch tools | Planning/heritage workflows, advanced summaries, imagery search, time slider and Street View are scheduled after Go Live and released incrementally.
Client feedback | Feedback is batched into scope approval, core-tool acceptance and consolidated UAT rather than requested for every tool.
Small-team model | The plan is mostly sequential, with only the data/API and frontend foundations overlapping where the backend and frontend developers can work independently.
Estimate alignment | Base estimate is 5,828 hours. The editable 20% contingency is 1,166 hours, producing 6,994 hours.
Scheduling | Change the yellow Project Start Date. Predecessors, weekdays and the Holidays sheet drive all dates.

## Validation (hidden)
Check | Formula | Expected
Total effort | 6994 | 6994
Base effort | 5828 | 5828
Go Live target | 46598 | 2027-07-30